中华人民共和国河北省审计厅

Hebei Provincial Audit Office of the People’s Republic of China

审  计  报  告

Audit Report

冀审外资报〔2015〕3号

HEBEI AUDIT REPORT〔2015〕NO.3

项目名称：   河北省世界银行贷款林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development

Project Financed by the World Bank

贷 款 号：    7939-CN

Loan No. :     7939-CN

项目执行单位：河北省林业外资项目管理中心

Project Entity:  Hebei Provincial Foreign-funded Forestry Projects Management Centre

会计年度：     2014

Accounting Year：2014

目   录

Contents

一、审计师意见	1

I. Auditor’s Opinion	.3

二、财务报表及财务报表附注	6

Ⅱ. Financial Statements and Notes to the Financial Statements	6

（一）资金平衡表	6

i. Balance Sheet	6

（二）项目进度表	8

ii. Summary of Sources and Uses of Funds by Project Component	8

（三）贷款协定执行情况表	11

iii. Statement of Implementation of Loan Agreement	11

（四）指定账户报表	12

iv. Designaed Account Statement	12

（五）财务报表附注	13

v. Notes to the Financial Statements	16

三、审计发现的问题及建议	19

III. Audit Findings and Recommendations	………………………… 21

一、审计师意见

审计师意见

河北省林业外资项目管理中心：

我们审计了河北省世界银行贷款林业综合发展项目2014年12月31日的资金平衡表及截至该日同年度的项目进度表、贷款协定执行情况表和专用账户报表等特定目的财务报表及财务报表附注（第6页至第18页）。

（一）项目执行单位及河北省财政厅对财务报表的责任

编制上述财务报表中的资金平衡表、项目进度表及贷款协定执行情况表是你中心的责任，编制专用账户报表是河北省财政厅的责任，这种责任包括：

1．按照中国的会计准则、会计制度和本项目贷款协定的要求编制项目财务报表，并使其实现公允反映；

2．设计、执行和维护必要的内部控制，以使项目财务报表不存在由于舞弊或错误而导致的重大错报。

（二）审计责任

我们的责任是在执行审计工作的基础上对财务报表发表审计意见。我们按照中国国家审计准则和国际审计准则的规定执行了审计工作，上述准则要求我们遵守审计职业要求，计划和执行审计工作以对项目财务报表是否不存在重大错报获取合理保证。

为获取有关财务报表金额和披露信息的有关证据，我们实施了必要的审计程序。我们运用职业判断选择审计程序，这些程序包括对由于舞弊或错误导致的财务报表重大错报风险的评估。在进行风险评估时，为了设计恰当的审计程序，我们考虑了与财务报表相关的内部控制，但目的并非对内部控制的有效性发表意见。审计工作还包括评价所选用会计政策的恰当性和作出会计估计的合理性，以及评价财务报表的总体列报。

我们相信，我们获取的审计证据是适当的、充分的，为发表审计意见提供了基础。

（三）审计意见

我们认为，第一段所列财务报表在所有重大方面按照中国的会计准则、会计制度和本项目贷款协定的要求编制，公允反映了河北省世界银行贷款林业综合发展项目 2014年12月31日的财务状况及截至该日同年度的财务收支、项目执行和专用账户收支情况。

本审计师意见之后，共同构成审计报告的还有两项内容：财务报表及财务报表附注和审计发现的问题及建议。

中华人民共和国河北省审计厅

2015年6月26日

地址：中国河北省石家庄市 友谊南大街195号

邮政编码：050051

电话：0311-88606354

传真：0311-88606120

I. Auditor’s Opinion

Auditor’s Opinion

To Hebei Provincial Foreign-funded Forestry Projects Management Centre:

We have audited the special purpose financial statements (from page 6 to page 18) of the Hebei Provincial Integrated Forestry Development Project Financed by the World Bank, which comprise the Balance Sheet as of December 31, 2014, the Summary of Sources and Uses of Funds by Project Component, the Statement of Implementation of Loan Agreement and the Special Account Statement for the year then ended, and Notes to the Financial Statements.

Project Entity and Hebei Provincial Finance Department’s Responsibility for the Financial Statements

The preparation of the Balance Sheet, the Summary of Sources and Uses of Funds by Project Component and the Statement of Implementation of Loan Agreement is the responsibility of your entity, while the preparation of the Special Account Statement is the responsibility of Hebei Provincial Finance Department, which includes:

i. Preparing and fair presenting the accompanying financial statements in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement;

ii. Designing, implementing and maintaining necessary internal control to ensure that the financial statements are free from material misstatement, whether due to fraud or error.

Auditor’s Responsibility

Our responsibility is to express an opinion on these financial statements based on our audit. We conducted our audit in accordance with the Government Auditing Standards of the People’s Republic of China and International Standards on Auditing. Those standards require that we comply with ethical requirements and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgment, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entities’ preparation and fair presentation of the financial statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

We believe that the audit evidence we have obtained is appropriate and sufficient to provide a basis for our audit opinion.

Opinion

In our opinion, the financial statements identified in the first paragraph present fairly, in all material respects, financial position of the Hebei Provincial Integrated Forestry Development Project Financed by the World Bank as of December 31, 2014, its financial receipts and disbursements, the project implementation and the receipts and disbursements of special account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement.

The audit report consists of the Auditor’s Opinion and two more parts hereinafter: Financial Statements and Notes to the Financial Statements, Audit Findings and Recommendations.

Hebei Provincial Audit Office of the People’s Republic of China

June 26 , 2015

Address:  No. 195, Youyi South Street, Shijiazhuang City, Hebei Province, P.R. China

Postcode: 050051

Tel.: 86-311-88606354

Fax: 86-311-88606120

二、财务报表及财务报表附注

Ⅱ. Financial Statements and Notes to the Financial Statements

（一）资金平衡表

i. Balance Sheet

资 金 平 衡 表

BALANCE SHEET

2014年12月31日

(As of December 31, 2014)

项目名称：世界银行贷款河北省林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development Project Financed by the World Bank

编报单位：河北省林业外资项目管理中心                                   货币单位：人民币元

Prepared by: Hebei Provincial Foreign-funded Forestry Projects Management Center    Currency Unit: RMB Yuan

| 资 金 占 用 Application of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance | 资 金 来 源 Sources of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 一、项目支出合计 Total Project Expenditures | 1 | 147,392,253.92 | 176,716,462.74 | 一、项目拨款合计 Total Project Appropriation Funds | 28 | 61,268,594.11 | 78,267,418.65 |  |
| 1. 交付使用资产 Fixed Assets Transferred | 2 | - | - | 二、项目资本与项目资本公积 Project Capital and Capital Surplus | 29 | - | - |  |
| 2. 待核销项目支出 Construction Expenditures to be Disposed | 3 | - | - | 其中:捐赠款 Including: Grants | 30 | - | - |  |
| 3. 转出投资 Investments Transferred-out | 4 | - | - | 三、项目借款合计 Total Project Loan | 31 | 92,223,632.56 | 100,447,017.95 |  |
| 4. 在建工程 Construction in Progress | 5 | 147,392,253.92 | 176,716,462.74 | 1. 项目投资借款 Total Project Investment Loan | 32 | 92,223,632.56 | 100,447,017.95 |  |
| 二、应收生产单位投资借款 Investment Loan Receivable | 6 | - | - | (1) 国外借款 Foreign Loan | 33 | 92,223,632.56 | 100,447,017.95 |  |
| 其中:应收生产单位世行贷款 Including: World Bank Investment Loan Receivable | 7 | - | - | 其中:国际开发协会 Including: IDA | 34 |  |  |  |
| 三、拨付所属投资借款 Appropriation of Investment Loan | 8 | - | - | 国际复兴开发银行 IBRD | 35 | 92,223,632.56 | 100,447,017.95 |  |
| 其中:拨付世行贷款 Including :Appropriation of World Bank Investment Loan | 9 | - | - | 技术合作信贷 Technical Cooperation | 36 | - | - |  |
| 四、器材 Equipment | 10 |  |  | 联合融资 Co- Financing | 37 | - | - |  |
| 其中:待处理器材损失 Including: Equipment Losses in Suspense | 11 | - | - | (2) 国内借款 Domestic Loan | 38 | - | - |  |
| 五、货币资金合计 Total Cash and Bank | 12 | 42,417,937.60 | 23,251,237.02 | 2. 其他借款 Other Loan | 39 | - | - |  |
| 1. 银行存款 Cash in Bank | 13 | 42,417,767.60 | 23,251,237.02 | 四、上级拨入投资借款 Appropriation of Investment Loan | 40 | - | - |  |
| 其中:专用账户存款 Including: Special Account | 14 | 6,490,793.57 | 11,573,940.79 | 其中:拨入世行贷款 Including: World Bank Loan | 41 | - | - |  |
| 2. 现金 Cash on Hand | 15 | 170.00 |  | 五、企业债券资金 Bond Fund | 42 | - | - |  |
| 六、预付及应收款合计 Total Prepaid and Receivable | 16 | 5,749,499.40 | 681,117.70 | 六、待冲项目支出 Construction Expenditures to be Offset | 43 | - |  | - |
| 其中:应收世行贷款利息 Including: World Bank Loan Interest Receivable | 17 | - | - | 七、应付款合计 Total Payable | 44 | 42,054,356.15 |  | 21,916,015.40 |
| 应收世行贷款承诺费 World Bank Loan Commitment Fee Receivable | 18 | - | - | 其中:应付世行贷款利息 Including: World Bank Loan Interest Payable | 45 | - |  | - |
| 应收世行贷款资金占用费 World Bank Loan Service- Fee Receivable | 19 | - | - | 应付世行贷款承诺费 World Bank Loan Commitment Fee Payable | 46 | - |  | - |
| 七、有价证券 Marketable Securities | 20 | - | - | 应付世行贷款资金占用费 World Bank Loan Service Fee Payable | 47 | - |  | - |
| 八、固定资产合计 Total Fixed Assets | 21 |  |  | 八、未交款合计 Other Payables | 48 | - |  | - |
| 固定资产原价 Fixed Assets, Cost | 22 |  |  | 九、上级拨入资金 Appropriation of Fund | 49 | - |  | - |
| 减:累计折旧 Less: Accumulated Depreciation | 23 | - | - | 十、留成收入 Retained Earnings | 50 | 13,108.10 |  | 18,365.46 |
| 固定资产净值 Fixed Assets, Net | 24 |  |  |  |  | - |  | - |
| 固定资产清理 Fixed Assets Pending Disposal | 25 | - | - |  |  | - |  | - |
| 待处理固定资产损失 Fixed Assets Losses in Suspense | 26 | - | - |  |  | - |  | - |
| 资金占用合计 Total Application of Fund | 27 | 195,559,690.92 | 200,648,817.46 | 资金来源合计 Total Sources of Fund | 51 | 195,559,690.92 |  | 200,648,817.46 |

（二）项目进度表

ii. Summary of Sources and Uses of Funds by Project Component

项 目 进 度 表（一）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅰ

本期截至2014年12月31日

(For the period ended December 31, 2014）

项目名称：世界银行贷款河北省林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development Project Financed by the World Bank

编报单位：河北省林业外资项目管理中心                                    货币单位：人民币元

Prepared by: Hebei Provincial Foreign-funded Forestry Projects Management Center    Currency Unit: RMB Yuan

|  | 本期 Current Period |  |  | 累计 Cumulative |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 本期计划额 Current Period Budget | 本期发生额 Current Period Actual | 本期完成比 Current Period % Completed | 项目总计划额 Life of PAD | 累计完成额 Cumulative Actual | 累计完成比 Cumulative % Completed |
| 资金来源合计 Total Sources of Funds | 46,804,000.00 | 25,222,209.93 | 53.89% | 272,000,000.00 | 178,714,436.60 | 65.70% |
| 国际金融组织贷款 International Financing | 25,576,000.00 | 8,223,385.39 | 32.15% | 136,000,000.00 | 100,447,017.95 | 73.86% |
| 1. 国际复兴开发银行 IBRD | 25,576,000.00 | 8,223,385.39 | 32.15% | 136,000,000.00 | 100,447,017.95 | 73.86% |
| 二、配套资金 Counterpart Financing | 21,228,000.00 | 16,998,824.54 | 80.08% | 136,000,000.00 | 78,267,418.65 | 57.55% |
| 1、省级配套 Province | 3,000,000.00 | 3,000,000.00 | 100.00% | 40,800,000.00 | 12,130,000.00 | 29.73% |
| 2、市级配套 Prefecture | 1,300,000.00 | 1,031,800.00 | 79.37% | 7,785,000.00 | 5,233,900.00 | 67.23% |
| 3、县级配套 County | 6,600,000.00 | 4,138,817.00 | 62.71% | 33,015,000.00 | 21,842,994.76 | 66.16% |
| 4、自筹资金 Self-raised Funds | 10,328,000.00 | 8,828,207.54 | 85.48% | 54,400,000.00 | 39,060,523.89 | 71.80% |
| 资金运用合计（按项目内容） Total Application of Funds (by Project Component) | 46,804,000.00 | 29,324,208.82 | 62.65% | 272,000,000.00 | 176,716,462.74 | 64.97% |
| 一、营造林工程 Forestation Project | 43,550,000.00 | 27,729,831.57 | 63.67% | 219,477,000.00 | 172,507,803.61 | 78.60% |
| 新造多功能人工林 New planted multifunctional forest |  | 27,729,831.57 |  |  | 172,507,803.61 |  |
| 修复现有人工林 Restore existing planted forest |  |  |  |  |  |  |
| 二、林权制度改革 Forest rights system reform | 293,000.00 | -9,550.00 | -3.26% | 1,846,000.00 | 330,450.00 | 17.90% |
| 实用技术培训推广 Pragmatic technology training |  | -9,550.00 |  |  | 86,950.00 |  |
| 扶持农民协会 Support peasant association |  |  |  |  | 143,500.00 |  |
| 其中：设备购置 Including: equipment purchase |  |  |  |  | 143,500.00 |  |
| 森林经营方案示范 Forrest operating program model |  |  |  |  | 100,000.00 |  |
| 林权改革支持 Forest rights reform support |  |  |  |  |  |  |
| 三、培训与技术服务 Training and technology service | 711,000.00 | 364,394.57 | 51.25% | 4,543,000.00 | 1,203,350.64 | 26.49% |
| 国内培训与考察 Homeland training and inspection |  | 170,775.00 |  |  | 698,275.00 |  |
| 国外培训与考察 Foreign training and inspection |  | 183,419.57 |  |  | 436,075.64 |  |
| 技术咨询 Technology consulting |  | 10,200.00 |  |  | 69,000.00 |  |
| 四、办公设备 Office equipments |  |  |  | 925,000.00 | 869,760.00 | 94.03% |
| 五、监测与评价 Monitor and evaluate |  | 534,996.30 |  | 2,250,000.00 | 1,122,126.33 | 49.87% |
| 六、项目管理 Project management | 2,250,000.00 | 394,669.22 | 17.54% | 11,050,000.00 | 1,361,861.92 | 12.32% |
| 七、其他支出 Other expenditures |  | 309,867.16 |  | 31,909,000.00 | -678,889.76 | -2.13% |
| 差异 Difference |  | -4,101,998.89 |  |  | 1,997,973.86 |  |
| 1.应收款变化 Change in Receivables |  | -5,068,381.70 |  |  | 681,117.70 |  |
| 2. 应付款变化 Change in Payables |  | 20,138,340.75 |  |  | -20,142,135.88 |  |
| 3.货币资金变化 Change in Cash and Bank |  | -19,166,151.87 |  |  | 21,477,357.50 |  |
| 4. 其他Other |  | -5,806.07 |  |  | -18,365.46 |  |

项 目 进 度 表（二）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅱ

本期截至2014年12月31日

(For the period ended December 31, 2014）

项目名称：世界银行贷款河北省林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development Project Financed by the World Bank

编报单位：河北省林业外资项目管理中心                                                                                          货币单位：人民币元

Prepared by: Hebei Provincial Foreign-funded Forestry Projects Management Center                                                  Currency Unit: RMB Yuan

| 项目内容 Project Component | 项目支出 Project Expenditure |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 累计支出 Cumulative Amount | 已交付资产 Assets Transferred |  |  |  | 在建工程 Work in Progress | 待核销项目支出Construction Expenditures to be Disposed | 转出投资Investments Transferred-out |
|  |  | 固定资产 Fixed Asset | 流动资产 Current Asset | 无形资产 Intangible Asset | 递延资产 Deferred Asset |  |  |  |
| 造林 Planting forest | 172,507,803.61 | - | - | - | - | 172,507,803.61 | - | - |
| 林权制度改革 Forest rights system reform | 330,450.00 | - | - | - | - | 330,450.00 | - | - |
| 培训与技术服务 Training and technology service | 1,203,350.64 |  |  |  |  | 1,203,350.64 |  |  |
| 办公设备 Office equipments | 869,706.00 |  |  |  |  | 869,706.00 |  |  |
| 监测与评价 Monitor and evaluate | 1,122,126.33 |  |  |  |  | 1,122,126.33 |  |  |
| 项目管理 Project management | 1,361,861.92 | - | - | - | - | 1,361,861.92 | - | - |
| 其他支出 Other expenditures | -678,889.76 | - | - | - | - | -678,889.76 | - | - |
| 合计 Total | 176,716,462.74 | - | - | - | - | 176,716,462.74 | - | - |

（三）贷款协定执行情况表

iii. Statement of Implementation of Loan Agreement

贷 款 协 定 执 行 情 况 表

STATEMENT OF IMPLEMENTATION OF LOAN AGREEMENT

本期截至2014年12月31日

(For the period ended December 31, 2014）

项目名称：世界银行贷款河北省林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development Project Financed by the World Bank

编报单位：河北省林业外资项目管理中心                                                       货币单位：美元/人民币元

Prepared by: Hebei Provincial Foreign-funded Forestry Projects Management Center             Currency Unit: USD/ RMB Yuan

| 类 别 Category | 核定贷款金额 Loan Amount 美元 USD | 本年度提款数 Current-period Withdrawals |  | 累计提款数 Cumulative Withdrawals |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 美元 USD | 折合人民币 RMB | 美元 USD | 折合人民币 RMB |
| - 国家林业局 SFA 本项目C部分中的国外培训与考察 Overseas training and study tours under Part C of the Project |  |  |  |  |  |
| 3、河北 Hebei Province | 19,950,000.00 | 1,289,278.28 | 7,889,093.80 | 14,365,593.72 | 87,903,067.95 |
| （a）本项目A部分的子贷款 Sub-financing under Part A of the Project | 19,026,300.00 | 1,171,985.11 | 7,171,376.89 | 13,951,097.48 | 85,366,765.46 |
| （b）本项目C部分中的货物、咨询服务、国内培训与考察 Goods, consulting services, domestic training and study tours under Part C of the Project | 923,700.00 | 117,293.17 | 717,716.91 | 414,496.24 | 2,536,302.49 |
| 7、先征费 Front-end Fee | 50,000.00 |  |  | 50,000.00 | 305,950.00 |
| 8、指定账户 Designated Account |  |  |  | 2,000,000.00 | 12,238,000.00 |
| 总计 Total | 20,000,000.00 | 1,289,278.28 | 7,889,093.80 | 16,415,593.72 | 100,447,017.95 |

（四）指定账户报表

iv. Designated Account Statement

指 定 账 户 报 表

DESIGNATED ACCOUNT STATEMENT

本期截至2014年12月31日

( For the period ended December 31, 2014）

项  目  名  称：世界银行贷款河北省林业综合发展项目

Project Name: Hebei Provincial Integrated Forestry Development Project Financed by the World Bank

世界银行贷款号： 7939-CN          开户银行名称：工商银行石家庄市新华支行

Loan No.  7939-CN                 Depository Bank: ICBC Shijiazhuang Xinhua Subbranch

账 号：04020 22709 00010 0603                                    货币种类：美元

Account  No. :  04020 22709 00010 0603                            Currency: USD

| A部分：本期指定账户收支情况 (Part A-Account Activity for the Period) |  | 金 额 Amount |
| --- | --- | --- |
| 期初余额 (Beginning Balance0 |  | 1,064,515.55 |
| 增加： (Add): |  |  |
| 本期世界银行回补总额 (Total Amount Deposited this Period by World Bank) |  | 1,289,278.28 |
| 本期利息收入总额（存入指定账户部分） (Total Interest Earned this Period if Deposited in Designated Account) |  | 848.72 |
| 本期不合格支出归还总额 (Total Amount Refunded to Cover Ineligible Expenditures) |  |  |
| 减少： (Deduct): |  |  |
| 本期支付总额 (Total Amount Withdrawn) |  | 463,146.69 |
| 本期未包括在支付额中的服务费支出 (Total Service Charges if not Included in Above Amount Withdrawn) |  | 20.00 |
| 期末余额 (Ending Balance) |  | 1,891,475.86 |
| B部分：指定账户调节 Part B-Account Reconciliation |  | 金 额 Amount |
| 1. 世行首次存款总额 (Amount Advanced by Reconciliation) |  | 2,000,000.00 |
| 减少： (Deduct:) |  | - |
| 2. 世界银行回收总额 (Total Amount Recovered by World Bank) |  | - |
| 3. 本期期末指定账户首次存款净额 Outstanding Amount Advanced to the Designated Account at the End of this Period |  | 2,000,000.00 |
| 4. 指定账户期末余额 Ending Balance of Designated Account |  | 1,891,475.86 |
| 增加： Add: |  |  |
| 5. 截至本期期末已申请报账但尚未回补金额 Amount Claimed but not yet Credited at the End of this Period |  | 0.00 |
| 申请书号 Application No. | 金额 Amount |  |
| 6. 截至本期期末已支付但尚未申请报账金额 (Amount Withdrawn but not yet claimed ) |  | 111,311.93 |
| 7. 服务费累计支出（如未含在5和6栏中） Accumulative Service Charges (If not Included in Item 5 .or 6.) |  | 110.00 |
| 减少： (Deduct |  |  |
| 8. 利息收入（存入指定账户部分） (Interest Earned -If Included in Designated Account) |  | 2,897.79 |
| 9. 本期期末专用账户首次存款净额 Total Advance to Designated Account Accounted for at the End of this Period |  | 2,000,000.00 |

（五）财务报表附注

财务报表附注

1.项目概况

河北省世界银行贷款林业综合发展项目贷款号为7939-CN，旨在通过该项目的实施，大力发展区域林业资源，增加项目区森林覆盖率，遏制沙化土地蔓延和进一步退化，改善当地生态环境，提高森林可持续经营水平，带动农村产业结构调整，促进地方经济发展，增加农民收入，并为其他地区推广具有重要公共产品效益的多功能人工林的可持续经营和管理模式提供示范。河北省世界银行贷款林业综合发展项目涉及4个市、17个县，主要项目内容包括在古黄河故道、永定河下游沙荒地区发展防风固沙林。营造多功能人工林2,4555.30公顷，机构服务能力支持及项目监测与评估。项目协议于2010年8月13日签订，建设期6年，其中，前4年造林，后2年抚育。项目计划总投资为人民币272,000,000.00元，其中世界银行贷款总额为20,000,000.00美元，折合人民币136,000,000.00元。

2. 财务报表编制范围

本财务报表的编制范围包括河北省林业外资项目管理中心、4个设区市项目办、17个县项目办的财务报表及省财政厅专用账户报表。

3. 主要会计政策

3.1本项目财务报表按照财政部《世界银行贷款项目会计核算办法》（财际字〔2000〕13号）的要求编制。

3.2会计核算年度采用公历年制，即公历每年1月1日至12月31日。

3.3本项目会计核算以 “权责发生制”作为记账原则，采用借贷复式记账法记账，以人民币为记账本位币。

3.4 按照中国人民银行2014年12月31日汇率，即USD1=人民币6.1190元。

4.报表科目说明

4.1项目支出

2014年项目支出人民币29,342,208.82元，累计支出人民币

176,716,462.74元，占总投资计划的64.97%。

4.2货币资金

2014年12月31日货币资金余额为人民币23,251,237.02元，其中专用账户存款折合人民币11,573,940.79元。

4.3预付及应收款

2014年12月31日余额为人民币681,117.70元。

4.4项目拨款

2014年12月31日余额为人民币78,267,418.65元，是省、市、县各级到位的配套资金(包括自筹资金)。

项目计划配套资金总额人民币136,000,000.00元，截至2014年12月31日到位配套人民币78,267,418.65元，占计划的57.55%，其中：省级计划配套资金总额人民币40,800,000.00元，累计到位人民币12,130,000.00元，占计划的29.73%；市级计划配套资金总额人民币7,785,000.00元，累计到位人民币5,233,900.00元，占计划的67.23%；县级计划配套资金总额人民币33,015,000.00元，累计到位人民币21,842,994.76元，占计划的66.16%；计划自筹配套资金人民币54,400,000.00元，实际到位人民币39,060.523.89元，占计划的71.80%。

4.5项目借款

2014年12月31日余额为人民币100,447,017.95元，其中：国际复兴开发银行贷款额为16,415,593.72美元，折合人民币100,447,017.95元。截至2014年12月31日，累计提取世界银行贷款资金为16,415,593.72美元，占贷款总额的73.86%。

4.6应付款

2014年12月31日余额为人民币21,916,015.40元，主要是应付未付造林主体的工程款。

5.专用账户使用情况

本项目专用账户设在工商银行石家庄市新华支行，账号为:04020 22709 00010 0603，币种为美元。专用账户首次存款 2,000,000.00美元。2014年年初余额1,064,515.55美元，本年度回补1,289,278.28美元，利息收入848.72美元，本年度支付463,146.69美元，服务费支出20.00美元,年末余额1,891,475.86美元。

Ⅴ. Notes to the Financial Statements

Notes to the Financial Statements

1. Project Overview

The Loan No. of Hebei Provincial Integrated Forestry Development Project Financedby the World Bank is 7939-CN. It aims to energetically develop local forest resources, increase forest coverage rates of the project area, keep desertification land from spreading and degenerating further, improve the local ecological environment, improve forest sustainable operating level, spur rural area industrial restructuring, promote local economic growth, increase the peasants' income and set an example for other areas a sustainable operating and managing pattern of multifunctional planted forest which has important public good benefits. The project involves 4 cities and 17 counties. The main project activities include developing windbreak and sand fixation forest along the old way of ancient Yellow River and Yongding River lower reaches sandy wasteland. Plant multifunctional forest 2,4555.30 hectare, establish service support and project monitor and evaluation system. The project agreement was signed on August 13, 2010; 6 years of duration, the first 4 years plant forests and the latter 2 years nurture them. The total investment plan of the project was RMB 272,000,000 yuan, among which the total World Bank loan amount was USD20,000,000 equivalent to RMB 136,000,000 yuan.

2. Consolidation Scope of the Financial Statements

Consolidation scope of the financial statements covers the financial statements of the project office of Hebei Province, 4 project offices of city level and 17 project offices of county level, as well as the Designated Account set in the Provincial Finance Department.

3. Accounting Policies

3.1 The Financial Statements of the project were prepared according to the requirements of Accounting Methods for the World Bank Financed Project（Caijizi[2000]No.13）.

3.2 In accounting practice, the Gregorian calendar year is adopted as the fiscal year from January 1 to December 31.

3.3 The accrual basis and the debit/credit double entry bookkeeping method are adopted. RMB is used as the recording currency of bookkeeping.

3.4 The exchange rate adopted in the financial statements was the exchange rate on December 31, 2014 of the People’s Bank of China, which is USD1= RMB6.1190 yuan.

4. Explanation of Subjects

4.1 Total Project expenditures

The project expenditure in 2014 was RMB29,342,208.82 yuan, and the cumulative expenditures were RMB 176,716,462.74yuan, which accounted for 64.97% of the total investment plan.

4.2 Cash and Bank

On December 31, 2014, the balance was RMB 23,251,237.02 yuan. And the funds in the Designated Account were converted to RMB 11,573,940.79 yuan.

4.3 Prepaid and Receivable

Its balance on December 31, 2014 was RMB 681,117.70 yuan.

4.4 Project Appropriation Funds

The balance on December 31, 2014 was RMB 78,267,418.65yuan, which were the counterpart funds allocated by all levels including the province, the city, the county and the planting entities (self-raised funds).

The total planned counterpart funds of this project were RMB136,000,000.00 yuan. By the end of 2014, RMB78,267,418.65yuan of the counterpart funds had been allocated, which accounted for 57.55% of the plan. The total planned counterpart funds for the province level were RMB40,800,000.00 yuan and the actual cumulative allocated funds were RMB12,130,000.00 yuan,29.73% of the plan; The total planned counterpart funds for the city level were RMB7,785,000.00 yuan and the actual cumulative allocated funds were RMB5,233,900.00 yuan, 67.23% of the plan; The total planned counterpart funds for the county level were RMB33,015,000.00 yuan and the actual cumulative allocated funds were RMB21,842,994.76yuan, 66.16%of the plan. The total planned self-raised counterpart funds were RMB 54,400,000.00 Yuan and the actual cumulative allocated funds were RMB 39,060,523.89 Yuan, 71.80% of the plan.

4.5 Project Loan

The balance on December 31, 2014 was RMB 100,447,017.95 yuan, including the IBRD loan USD 16,415,593.72, equivalent to RMB 100,447,017.95yuan.

By the end of December 31, 2014, accumulated USD 16,415,593.72of the World Bank loan had been withdrawn, accounting for 73.86%of the total.

4.6 Payable

The balance on December 31, 2014 was RMB 21,916,015.40 yuan, mainly payable account for planting forests to the planting entity.

5. Designated Account

The Designated Account of this project is set in ICBC Shijiazhuang Xinhua Subbranch, with the account number of 04020 22709 00010 0603, and USD as currency Unit. The initial Deposit of the Special Account is USD 2,000,000.00. The beginning balance of 2014 was USD1,064515.55 and the reimbursement in the year was USD1,289,278.28 . This year the interest earned was USD 848.72, the disbursement was USD 463,146.69, and the service charge of the year was USD 20.00. Thus, the ending balance was USD 1,891,475.86.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况。我们发现存在如下问题：

违反国家法规或贷款协定的问题

配套资金未及时足额到位。

截至2014年12月31日，该项目共有16个县配套资金6,410,830.90元未到位。明细情况如下表：

| 项目市县 | 配套资金 | 计划数 | 到位数 | 完成% | 差额 |
| --- | --- | --- | --- | --- | --- |
| 永年 | 市级 | 220,000.00 | 0.00 | 0.00% | 220,000.00 |
| 景县 | 市级 | 120,000.00 | 0.00 | 0.00% | 120,000.00 |
| 小计 |  | 340,000.00 | 0.00 | 0.00% | 340,000.00 |
| 永年 | 县级 | 100,000.00 | 0.00 | 0.00% | 100,000.00 |
| 邱县 | 县级 | 340,000.00 | 0.00 | 0.00% | 340,000.00 |
| 肥乡 | 县级 | 620,000.00 | 200,000.00 | 32.26% | 420,000.00 |
| 曲周 | 县级 | 470,000.00 | 461,500.00 | 98.19% | 8,500.00 |
| 馆陶 | 县级 | 730,000.00 | 558,825.00 | 76.55% | 171,175.00 |
| 大名 | 县级 | 530,000.00 | 249,350.00 | 47.05% | 280,650.00 |
| 广宗 | 县级 | 230,000.00 | 0.00 | 0.00% | 230,000.00 |
| 临西 | 县级 | 220,000.00 | 65,000.00 | 29.55% | 155,000.00 |
| 武邑 | 县级 | 310,000.00 | 263,400.00 | 84.97% | 46,600.00 |
| 景县 | 县级 | 20,000.00 | 0.00 | 0.00% | 20,000.00 |
| 永清 | 县级 | 370,000.00 | 342,292.00 | 92.51% | 27,708.00 |
| 文安 | 县级 | 500,000.00 | 0.00 | 0.00% | 500,000.00 |
| 大城 | 县级 | 600,000.00 | 0.00 | 0.00% | 600,000.00 |
| 小计 |  | 5,040,000.00 | 2,140,367.00 | 42.47% | 2,899,633.00 |
| 邱县 | 自筹资金 | 443,700.00 | 0.00 | 0.00% | 443,700.00 |
| 肥乡 | 自筹资金 | 802,000.00 | 0.00 | 0.00% | 802,000.00 |
| 曲周 | 自筹资金 | 963,000.00 | 0.00 | 0.00% | 963,000.00 |
| 威县 | 自筹资金 | 470,700.00 | 241,864.60 | 51.38% | 228,835.40 |
| 临漳 | 自筹资金 | 1,263,200.00 | 1,145,975.92 | 90.72% | 117,224.08 |
| 永清 | 自筹资金 | 995,200.00 | 855,730.00 | 85.99% | 139,470.00 |
| 文安 | 自筹资金 | 759,000.00 | 467,042.52 | 61.53% | 291,957.48 |
| 大城 | 自筹资金 | 506,200.00 | 452,589.06 | 89.41% | 53,610.94 |
| 广阳 | 自筹资金 | 131,400.00 | 0.00 | 0.00% | 131,400.00 |
| 小计 |  | 6,334,400.00 | 3,163,202.10 | 49.94% | 3,171,197.90 |
| 合计 |  | 11,714,400.00 | 5,303,569.10 | 45.27% | 6,410,830.90 |

上述行为违反了财政部《国际金融组织贷款赠款项目财务管理暂行办法》（财际〔2011〕10号）“第十一条各出资部门应按照协议约定履行出资责任。项目单位应当按照有关协议以及项目评估报告的要求，及时足额筹集配套资金”的规定。

根据《审计署办公厅关于国际金融组织贷款项目审计处理指导原则的通知》（审办外资发〔1999〕51号）第五条“对配套资金不落实、不能按时到位的，应责成有关部门制定详细的资金到位计划，限期到位。”的规定，建议你中心加强项目管理，积极落实各级配套资金，确保项目按计划完成。你中心已接受审计建议。

III. Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management. We found the following issues:

Non-compliance with state laws and regulations or the applicable provisions of the loan agreement

Counterpart funds were not in place in full and on time

By the end of December 31, 2014, RMB 6,410,830.90 Yuan of counterpart fund which should be supplied by 16 counties had not reached the project account. The detailed information are listed in the following table：

Currency Unit: RMB Yuan

| Unit | Counterpart Funds | Planned Amount | Received Amount | % of Plan | Amount Due |
| --- | --- | --- | --- | --- | --- |
| Yongnian County | prefecture | 220,000.00 | 0.00 | 0.00% | 220,000.00 |
| Jing County | prefecture | 120,000.00 | 0.00 | 0.00% | 120,000.00 |
| Subtotal |  | 340,000.00 | 0.00 | 0.00% | 340,000.00 |
| Yongnian County | County | 100,000.00 | 0.00 | 0.00% | 100,000.00 |
| Qiu County | County | 340,000.00 | 0.00 | 0.00% | 340,000.00 |
| Feixiang County | County | 620,000.00 | 200,000.00 | 32.26% | 420,000.00 |
| Quzhou County | County | 470,000.00 | 461,500.00 | 98.19% | 8,500.00 |
| Guantao County | County | 730,000.00 | 558,825.00 | 76.55% | 171,175.00 |
| Daming County | County | 530,000.00 | 249,350.00 | 47.05% | 280,650.00 |
| Guangzong County | County | 230,000.00 | 0.00 | 0.00% | 230,000.00 |
| Linxi County | County | 220,000.00 | 65,000.00 | 29.55% | 155,000.00 |
| Wuyi County | County | 310,000.00 | 263,400.00 | 84.97% | 46,600.00 |
| Jingxian County | County | 20,000.00 | 0.00 | 0.00% | 20,000.00 |
| Yongqing County | County | 370,000.00 | 342,292.00 | 92.51% | 27,708.00 |
| Wenan County | County | 500,000.00 | 0.00 | 0.00% | 500,000.00 |
| Dachen County | County | 600,000.00 | 0.00 | 0.00% | 600,000.00 |
| Subtotal |  | 5,040,000.00 | 2,140,367.00 | 42.47% | 2,899,633.00 |
| Qiuxian County | Self-raised | 443,700.00 | 0.00 | 0.00% | 443,700.00 |
| Feixiang County | Self-raised | 802,000.00 | 0.00 | 0.00% | 802,000.00 |
| Quzhou County | Self-raised | 963,000.00 | 0.00 | 0.00% | 963,000.00 |
| Wei County | Self-raised | 470,700.00 | 241,864.60 | 51.38% | 228,835.40 |
| Linzhang County | Self-raised | 1,263,200.00 | 1,145,975.92 | 90.72% | 117,224.08 |
| Yongqing County | Self-raised | 995,200.00 | 855,730.00 | 85.99% | 139,470.00 |
| Wenan County | Self-raised | 759,000.00 | 467,042.52 | 61.53% | 291,957.48 |
| Dacheng County | Self-raised | 506,200.00 | 452,589.06 | 89.41% | 53,610.94 |
| Guangyang County | Self-raised | 131,400.00 | 0.00 | 0.00% | 131,400.00 |
| Subtotal |  | 6,334,400.00 | 3,163,202.10 | 49.94% | 3,171,197.90 |
| Total |  | 11,714,400.00 | 5,303,569.10 | 45.27% | 6,410,830.90 |

The above practice violated the provision of Article 11 in Interim Financial Management Methods for International Financial organization Loan and Grant Projects (MOF ID [2011] No.10), which stipulates that all of the investment units shall fulfill the obligation of contribution in accordance with the agreement, the project units shall raise counterpart funds in full amount and on time in accordance with the related agreements and the requirements of the project assessment report. We suggested your center to strengthen the project management, actively implement various counterpart funds and ensure the project be completed on schedule. The audit recommendations have been accepted by your center.

It is stipulated in Article 5 of the “Notice by the General Office of the National Audit Office on the Guidelines on Implementation of Audits of Projects Utilizing Loans from International Financial Institutions” (NAO Foreign Investment Doc. No. [1999]51) that “the concerned departments shall be instructed to develop a detailed plan and establish a deadline for making available the counterpart fund that is not made available on time.” According to this stipulation,We suggested your center to strengthen the project management, actively implement various counterpart funds and ensure the project be completed on schedule. Your center has accepted our audit suggestion.